## Slide 1: WorkView R2 COG APAC SIT Planning Meeting
Nov 2016
Version 1.0
21 November, 2016

## Slide 2
63%
Test Execution Completion
2145
Pending Test Cases to be executed
3662
37%
Pass % against Overall Test Cases
1115
Total
Open Defects
59%
Pass Rate against executed Test Cases
363
Total Open P1 & P2 Defects
14 Days
Available Calendar Days - 8th Dec Completion
Total Test Cases Executed
Key Headlines
SIT Execution is in Progress for APAC components (excl. BIRI, CI, Complaints, General Files) and Test Execution Percentage is at 63% & Overall Pass Percentage has increased to 37%.
The build (23/24) enabled 283 Test Cases for execution out of planned ~1713 test cases. We have completed the execution for the enabled 283 test cases.
  Meridian & Its dependent Components: ~278 Test Cases - Data Load functionalities (Meridian  WorkView) working and Data Extract (WorkView  Meridian) still has issues.
  WorkLoad (Partial Deployment): ~5 Test Cases
Defect Closure: Out of 37 defects delivered - 23 (2 P1, 13 P2, 6 P3, 2 P4) defects were Closed. 12 (5 P1, 6 P2, 1 P3, 0 P4) Defects were Re-Opened and 2 Defects (1 P1, 0 P2, 1 P3, 0 P4) are in Retest Dependency.
Retested ~879 Open Defects to check for associated Defect Fixes/Sporadic Errors/Non-Reproducible errors - We have closed ~103 defects (2 P1, 47 P2, 54 P3) in total as they are resolved in the latest builds
Component Delivery Status (As of 21st Nov 2016)
WorkView R2 COG APAC - Testing Summary
Test Execution Progress
Components / Interfaces Delivered | Components / Defects Not Delivered in Nov 15th / 17th Nov Build | Component Delivery Plan for Nov 22nd Build
Policy Claims Search Templates Security PAP - 19 Broker Account Certificate ACRS System 6 Indexing & Document Actions Meridian (Partial) Chubb Compliance (Partial) Workload Button (Partial) | Policy Workflow - 373 Test Cases ( #8029, #8161, #6842) Claim Workflow - 292 Test Cases (#8226, #6842, #8557 ) Doc Gen - 258 Test Cases Document Actions Defect - 126 Test Cases #8222 PDP Services (Partial Deployment) - 53 Test Cases ACC - 121 Test Cases Workload #8560 - 33 Test Cases Search (Meridian Dependent) - 29 TC Chubb Compliance(Partial) #8603 - 60 TC Meridian Integration #8696, #8682 - 85 Test Cases Total Impacted Test Cases: 1430 TC | PDP Services Document Ingestion from Meridian Meridian (Data Extract: WorkView  Meridian) Doc Gen Fix Chubb Compliance (Pending Functionalities) ACC Workload (Pending Functionalities) Defect Fix for Critical and key high defects shared

## Slide 3
Revised Burn Down & Execution Plan
Revised Burn Down (As of 21st Nov 2016)
Key Success Factors to achieve the above test execution plan
We are foreseeing Overall 589 Open P1 & P2 defects by 30th Nov 2016.
The Average P1 & P2 Defect Closure / week needs to be maintained at 30 / week until 30th Nov 2016 and then to be increased to 60 defects / week from 1st Dec 2016.
By achieving the above defect fix rate, we are expecting the pass percentage to be at ~80% Pass by 12th Jan 2016 for APAC region (excluding BIRI, CI, General Files, Complaints).
  We can complete the pending 2145 Test Cases with 14 functional testers working until 8th Dec 2016.
Chart: Planned Vs. Actual - Burndown Based on Build Drop / Defect Fixes Plan
| 26-Sep | 17-Oct | 20-Oct | 27-Oct | 1-Nov | 3-Nov | 5-Nov | 8-Nov | 10-Nov | 15-Nov | 17-Nov | 22-Nov | 24-Nov | 29-Nov | 01-Dec | 8-Dec | 15-Dec | 22-Dec | 29-Dec | 5-Jan | 12-Jan
Base Plan (14 Oct) | 5807 | 4352 | 3744 | 1766 | 1766 | 168 | 168 | 168 | 47 | 47 | 9 | 9 | 9 | 0
Revised Plan (17 Nov) | 5807 | 4352 | 3744 | 3436 | 3436 | 3436 | 3436 | 2642 | 2428 | 2428 | 2145 | 2145 | 9 | 0
Actual QA Burn Down | 5807 | 4352 | 3744 | 3436 | 3436 | 3436 | 3436 | 2814 | 2594 | 2454 | 2145 | 2145
Pass Rate (%) | 0 | 0.14 | 0.2 | 0.24 | 0.24 | 0.24 | 0.25 | 0.32 | 0.33 | 0.33 | 0.36 | 0.37369 | 0.5731 | 0.58937 | 0.62037 | 0.65137 | 0.68237 | 0.71336 | 0.74436 | 0.77536 | 0.80635

## Slide 4
SIT Progress at Component Level
 | Work View - R2 COG Components | Test Execution % | Pass % Against Total Test Cases | Overall Open Defects | Open P1 & P2 | Test Cases | Overall Status | 
 |  |  |  |  |  |  | Pass | Fail
Workflows & UI Elements | Policy | 69% | 39% | 183 | 66 | 1316 | 507 | 395
 | Claims | 57% | 33% | 111 | 51 | 636 | 212 | 152
 | Certificate (Child Policy) | 100% | 59% | 66 | 22 | 46 | 27 | 19
 | Correspondent | 87% | 72% | 38 | 10 | 123 | 88 | 19
 | Broker | 100% | 32% | 23 | 0 | 25 | 8 | 17
 | Account | 96% | 78% | 28 | 1 | 23 | 18 | 4
 | Indexing | 100% | 77% | 58 | 25 | 200 | 154 | 46
 | File Actions | 100% | 74% | 11 | 2 | 66 | 49 | 17
 | Document Actions | 42% | 18% | 44 | 15 | 238 | 44 | 56
 | Workbasket/UI | 98% | 45% | 134 | 33 | 103 | 46 | 55
 | Alerts & Notes/Audit | 100% | 59% | 27 | 7 | 73 | 43 | 30
 | Flags and Milestones | 100% | 45% | 11 | 3 | 49 | 22 | 27
 | Get Next | 100% | 0% | 4 | 3 | 10 | 0 | 10
 | Workload | 13% | 0% | 4 | 1 | 38 | 0 | 5
Search Templates | Policy Search Templates | 97% | 52% | 76 | 3 | 197 | 102 | 89
 | Claim Search Templates | 84% | 24% | 36 | 8 | 170 | 40 | 102
 | Correspondent Search | 100% | 0% | 2 | 2 | 8 | 0 | 8
 | Certificate Search | 100% | 10% | 5 | 2 | 20 | 2 | 18
 | Core Search Templates | 76% | 7% | 24 | 8 | 55 | 4 | 38
Ingestion | Datacap scanning | 100% | 88% | 2 | 2 | 141 | 124 | 17
 | Upload Document | 100% | 70% | 11 | 4 | 30 | 21 | 9
 | Save and Send | 53% | 42% | 3 | 2 | 60 | 25 | 7
 | WorkView Print | 100% | 75% | 2 | 1 | 24 | 18 | 6
 | Drag & Drop | 100% | 50% | 18 | 12 | 88 | 44 | 44
 | ACRS Documents | 100% | 0% | 1 | 1 | 26 | 0 | 26
 | PBE Documents | 0% | 0% | 0 | 0 | 23 | 0 | 0
 | CLEX Report | 0% | 0% | 0 | 0 | 56 | 0 | 0
 | FACRI Report | 0% | 0% | 0 | 0 | 35 | 0 | 0
 | Generic Email Broker | 100% | 8% | 27 | 23 | 76 | 6 | 70
Security | PAP & PDP | 39% | 34% | 18 | 7 | 782 | 269 | 37
Viewer | Daeja Viewer | 87% | 34% | 6 | 4 | 125 | 43 | 66
Doc Gen | Barcode Generation | 63% | 54% | 10 | 2 | 89 | 48 | 8
 | Document Generation | 28% | 17% | 39 | 21 | 357 | 60 | 39
Interfaces | ACRS | 66% | 57% | 6 | 0 | 44 | 25 | 4
 | System 6 | 81% | 70% | 4 | 2 | 53 | 37 | 6
 | Chubb Compliance Check | 0% | 0% | 2 | 2 | 60 | 0 | 0
 | Meridian | 59% | 34% | 28 | 9 | 221 | 75 | 56
 | ACC | 0% | 0% | 0 | 0 | 121 | 0 | 0

## Slide 5
Top 30 Priority Defects
Defect ID | Defect Summary | Priority | Component Name | QA Suggested Planned Fix Date | VEGA Updates
8223 | Policy¦ While performing "Accepted" action through File Action for work item at Quote response step, unable to proceed further for legal and compliance validation. | 1 - Critical | Policy | 21/11/2016 | 
8029 | Policy¦ List of actions are not displayed for the work item at bind policy step | 1 - Critical | Policy | 21/11/2016 | 
8222 | User is unable to perform copy/move/link action for a document, as for all actions "Paste" option is disabled under tree view | 1 - Critical | Document Actions | 21/11/2016 | 
8226 | Claims: File actions are not present while creating a claim with an associated workitem, | 1 - Critical | Claims | 21/11/2016 | 
7044 | Policy UI: Unexpected error is displayed when Workflow actions is selected for a workitem in prospect step | 2 - High | Policy | 21/11/2016 | 
7441 | Claims ¦ Unable to grant approval in 'Approval Request' workitem , unexpected error is seen | 2 - High | Claims | 21/11/2016 | 
8557 | R2 COG: Claims: Request time out message is getting displayed while clicking on the Registraion Workbasket and workitems are not displayed | 1 - Critical | Claims | 21/11/2016 | 
8560 | Work Load : Long running scripts displayed when clicked on the Work Load tab. | 1 - Critical | Workload | 21/11/2016 | 
8603 | R2 COG ¦ Chubb Compliance ¦ Automatic sanction check is not getting triggered while creating a new correspondent. | 1 - Critical | Chubb Compliance Link | 21/11/2016 | 
8618 | R2 COG ¦ Chubb compliance ¦ User is unable to trigger Manual Sanction check on a correspondent file as "Sanction Check" file action is missing under the Correspondent file. | 1 - Critical | Chubb Compliance Link | 21/11/2016 | 
8161 | Policy : Unable to Perform Legal and Compliance Validation in Policy Renewal Work Flow ¦ Renewal work item is not getting displayed in Compliance workbasket at Legal & Compliance Validation step | 1 - Critical | Policy | 21/11/2016 | 
7273 | Re-assign ¦ Reassign Reason dropdown is not showing mandatory fields to the user for reassign action | 2 - High | Policy | 21/11/2016 | 
7477 | Claims ¦ User is unable to perform "Wait for response" action on the Recovery parallel work item as "Claimant" and "Loss Description" fields are not reflecting from the main claim file | 2 - High | Claims | 21/11/2016 | 
7640 | Certificate(Child Policy) ¦ 'Declined' file action is not available for Further information request worktime on certificate file. | 2 - High | Certificate (Child Policy) | 21/11/2016 | 
8178 | Certificate: While selecting new workitem option for a certificate file further information request worktime option is not displayed. | 2 - High | Certificate (Child Policy) | 21/11/2016 | 
6400 | Correspondent : Correspondent Search option is not available in the Search Template | 2 - High | Correspondent Search | 21/11/2016 | 
8037 | Unexpected Error' message is displayed when user opens any result from 'Policy Work Item Search' | 2 - High | Core Search Templates | 21/11/2016 | 
8192 | Notes ¦ Unable to add note in Notes/audit tab inside a workitem as it is disabled | 2 - High | Alerts & Notes/Audit | 21/11/2016 | 
6856 | Search Template :"File Note", "Workitem Note" and "Document Note" and "Workitem" template is not available in the search tab. | 2 - High | Core Search Templates | 21/11/2016 | 
6640 | Policy :'Target Date', 'Exit' and 'Close-created in error' file actions are not present under workitem actions for policy file. | 2 - High | Policy | 21/11/2016 | 
7202 | Certificate : While creating a Certificate file with process enrollment workitem, the workitem is not getting created. | 2 - High | Certificate (Child Policy) | 21/11/2016 | 
7685 | Policy: When the user performs “NTU” action for a process submission workitem,the process submission workitem is displayed in the open workitem node instead of closed workitem node. | 2 - High | Policy | 21/11/2016 | 
7514 | Policy : Unexpected error is getting displayed while Performing "Close" action for multiline submission workitem. | 2 - High | Policy | 21/11/2016 | 
8114 | Indexing: Document type is not displaying the exact values in the drop down according to the file type and folder type selected for policy file. | 2 - High | Indexing | 21/11/2016 | 
6864 | Search Template ¦ Unable to open any document from search results screen in document search template | 2 - High | Core Search Templates | 21/11/2016 | 
6652 | Policy :'Clone' and 'Link Correspondent' action is not available under the File Actions after opening or creating any policy file. | 2 - High | Policy | 21/11/2016 | 
7186 | Certificate(Child Policy)¦ Clone, Show hyperlink ,link file, link correspondent, exit file actions are not present for certificate file. | 2 - High | Certificate (Child Policy) | 21/11/2016 | 
6589 | Certificate: Unable to close the Process Enrollment Work item by clicking on "Close-Created in Error" from the file Actions, "Un expected error" message is displayed. | 2 - High | Certificate (Child Policy) | 21/11/2016 | 
7482 | Claims ¦ "Recovery" worktime is not getting created under "Adjudication" workbasket | 2 - High | Claims | 21/11/2016 | 
7574 | Policy: Complete action is not present for peer review workitem. | 2 - High | Policy | 21/11/2016 | 

## Slide 6: Thank You