## Slide 1: Work View CGM - High Level Plan & Test Approach
Chubb Global Market
Version1.6

## Slide 2
Agenda
High Level Timelines Overview
CGM Overview & Interface Test Approach
CGM Business Workflow & Component Matrix
CGM Test Scope, Process & Deliverables
CGM Quality Gates & Defect Management Process

## Slide 3
Work View CGM SIT - High Level Testing Plan
Build 1A + 1B - SIT Window
Data Migration
* The above timelines was defined based on the latest build plan. Please refer the appendix
Drop 1
Drop 2
UAT
Go Live
Cycle 1
Cycle 2

## Slide 4
CGM SIT Timelines - Key Updates & Dependencies
Dependencies | Key Dates | Ownerships
SIT Environment Availability - Integrated with all the Interface components and necessary access rights (Subscribe and WebCon) - Functional Testing | 18th Apr 2016 | Environment Team
SIT Data Migration Environment (Vega UI, Data moved to Environment and its corresponding documents available in the environment). Development completed for Data migration. | 13th Jun 2016 | Migration Team, Environment Team
Common Best Practises to be leveraged in build / deployment / environment readiness testing:
Overall build/Release plan creation & it’s adherence
Availability of Test environment Co-ordinator and existence of process to plan and monitor the usage and implement the access related requirements.
Deployment should be planned and max 2 in week to improve the code stability. (Critical defects are exception)
Build Note is sent for every deployment, it contains testing consideration section filled based on the developer impact analysis
The high level timelines are given based on Work View CGM Build Plan and will change based on the build plan.
Test Design will be completed by 06th May 2016; Test Execution will commence from 10th May 2016.
2 Cycles in each Code Drop; 100% - 1st Cycle and 40% in 2nd Cycle including Defect Retesting. The testing in Cycle 2 with 40% of test cases being executed with an assumption of 30% failure rate in Cycle 1 & 10% regression cases.
1 Cycle of End to End Testing is planned for CGM business functionalities after the completion of 1A + 1B build.
Data Migration Testing - Cycle 1 & Cycle 2 testing will be performed on Migration Test Environment with Work View by comparing with source system.
SIT Timelines - Key Updates
SIT Timelines - Dependencies

## Slide 5: CGM High Level Overview & Interface Test Approach
CHUBB Global Market

## Slide 6
CGM High Level Overview
File Net
Biz Talk ESB
Subscribe
WebCon Gateway
Policy Data
Endorsement Message
Send ACORD Message
Policy Workflow
Policy Endorsement Data
Message
APP DB
View / Read Policy Data
ICC
Endorsement Message
(Document)
Ingestion Components
Work View - Vega UI
Daeja Viewer
Create Peer Review WI
Create Risk Registration
Create Rate Monitoring WI
Create Cover Holder WI
Create FAC Admin WI
Create PC/QC WI
Create Exception Authorization
Create Contract Certainty WI
Query to Underwriter
Query to Messaging Team
Create Endorsement WI
DCS Message
Scan to Xchanging WI
Internal CGM Users
DataCap Scanning, Fax, Email, Upload, Drag & Drop
Indexing
Workflow

## Slide 7
CGM Interface Testing - Subscribe & WebCon Gateway
Systems | Test Approach | Activity | Owner | Dependencies
Subscribe | Creation of Master and Line Policies/Claim in Subscribe System. Creation of Subsequent Policy Transaction such as Renewal, Endorsement, Cancellation , New Business | Data Creation / Prod. Data Feed | SIT Team | The Subscribe system needs to be integrated with Work View Via BizTalk & available for data creation on or before 10th May 2016
 | Scheduled Batch Process to Update / Create Policy /Claim Files into Work View in every 5 Mins. Web Service Connectivity to create the New Submissions in Work View System as and when it gets created in Subscribe System | Run Batch Job / Web Service | Work View Dev Team | The necessary support from Development Team for running the batch process / maintaining the web service active to retrieve & update details from Subscribe to Work View.
 | Validating the Policy/Claim and its subsequent transactions in Work View that are created in Subscribe System | Testing | SIT Team | Access for Work View / Subscribe needs to be provided to SIT Team for validation purpose.
 | Validation of document ingestion process Creation & Validation of CGM Business Workflows Validation of document indexing & linking to a Policy/Claim file | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team
WebCon Gateway | E-Endorsement Message Set up in WebCon Message Gate Way Placing of Document slip which needs to be routed to Xchanging Validation of Acknowledgement notification in WebCon once after the successful creation Work Item in Work View | WebCon | SIT Team | WebCon Message Gateway should be integrated with Work View. WebCon gateway and its web service should be up and running.
 | Validation of Endorsement Work item created in Work View System once after receiving the Message from WebCon Indexing, Re-assign and Complete the Work item in Work View System | Testing | SIT Team | WebCon gateway and its web service should be up and running Test Data will be created in the XML feed File
*Knowledge Transition to be planned to SIT Team for Test Data Creation

## Slide 8
CGM Interface Data Feed Process
CGM Interfacing Functionality | Source System | Destination System | Communication Mode for Data Flow
View Read Only data from Subscribe in Work View Screen | Subscribe | Work View | Real Time - On Demand
*Quote-Policy Reference Validation | Subscribe | Work View | Near Real Time (2 mins)
*Search Policy Reference – In Progress | Subscribe | Work View | Real Time - On Demand
Rate Monitoring Process | Subscribe | Work View | Scheduled – Near Real time
Peer Review Event Handlers | Subscribe | Work View | Scheduled
Synchronize policy, policy re-reference data | Subscribe | Work View | Scheduled
Receive ACORD Message e- Endorsement / Acknowledgements | WebCon | Work View | Scheduled - Near Real Time
Receive ACCORD Message - Placement message from DCS via WebCon gateway And Route it to the risk registration team within Work View as work item | WebCon | Work View | Scheduled - Near Real Time
Send ACORD Message - Request For Information/ Request For Negotiation etc. | Work View | WebCon | Real Time - On Demand
Send the scan image of the UW slip and send it to Xchanging via WebCon Gateway | Work View | WebCon | Real Time - On Demand
*Details to be updated after Sign-off of the Functional Specification

## Slide 9
CGM Test Data Requirement to Subscribe Team
S.No | Transaction Type | Test Data Specification | *No. of Files (Cycle 1) | *No. of Files (Cycle 2) | Remarks
1 | All Transaction Type | Quote/Policy Files and Claim Files with Different transaction and Status | 250 | 130 | Cycle-1: Required Policy Batch feed of Subscribe on 20th May 2016 Cycle-2: Required Policy Batch feed of Subscribe on 15th Jun 2016.
2 | Submission Quote | Quote creation in Subscribe for multiple LOBs | 50 | 30 | Subscribe team to provide the Files with requested data specification / required access to Subscribe System to perform the necessary transactions
 |  | Quote Submission with different Premium details [Rate Monitoring] | 50 | 30 | 
3 | New Business | New Business Policy with Partial/Live Status [Peer Review] | 50 | 30 | 
 |  | Policy set with FAC Alert Flag as “YES” [FAC Admin] | 50 | 30 | 
 |  | Creation of New Business Policy with Live Status [Cover Holder] Update the Policy Contact details [Cover Holder] | 50 | 30 | 
4 | Renewal | Renewal Quote Creation in Subscribe where Premium should Exceed the UWR Authority Limit [Policy Processing WI] | 50 | 30 | 
 |  | Creation of New Business Policy which is 120 days Due for renewal [Cover Holder Renewal Binder] | 50 | 30 | 
 |  | Renewal Quote Submission with different premium details [Rate Monitoring] | 50 | 30 | 
 |  | Renewal Policy with Partial/Live Status [Peer Review] | 50 | 30 | 
5 | Endorsement | Endorsement Creation on New Business Policy [Rate Monitoring Work Item] | 50 | 30 | 
 |  | Endorsement Creation on Renewal Policy [Rate Monitoring Work Item] | 50 | 30 | 
 |  | Creation of Endorsement in which update the contact details [Cover Holder] | 50 | 30 | 
 |  | Policy Set with FAC Alert Flag as “YES” [FAC Admin] | 50 | 30 | 
All the Cycle1 Files to be available by 20th May 2016 & for Cycle2 by June 15th 2016

## Slide 10
Out of Scope
Data Migration Strategy will be covered separately
Performance Testing
Webcon Testing is out of scope. Test Data will be created in XML feed files and tested in Work View.

## Slide 11: CGM Business Workflow & Component Matrix
CHUBB Global Market

## Slide 12
CGM Business Workflow - Policy Processing & Contract Certainty
Workflow | Test Approach | Activity | Owner | Dependencies
Authorisation Exception WI | Manual creation of Authorisation Exception WI in WorkView WI Initiation from Policy File | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team Work View user should be set up with the appropriate role to access the work item
 | Work Item validation in WorkView UI and Indexing with Policy/Quote File interfaced from Subscribe System | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team Work View user should be set up with the appropriate role to access the work item.
 | Validation of workflow actions (pend, un pend, reassign, etc.) | Testing | SIT team | Access for Work View system needs to be provided to SIT Team Work View user should be set up with the appropriate role to access the work item.
Contract Certainty | Manual work item creation in Work View System upon receiving the Quote / Slip. | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team Work View user should be set up with the appropriate role to access the work item.
 | Indexing of work item with respective Policy / Quote details received from Subscribe System | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team Work View user should be set up with the appropriate role to access the work item.
 | Validation of workflow actions (pend, un pend, reassign, etc.) | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team Work View user should be set up with the appropriate role to access the work item.
PS: Mode of Interface data flow is not yet frozen. The CGM Business Workflow & Component Matrix is updated based on latest Functional Spec v0.

## Slide 13
CGM Business Workflow - Peer Review & FAC Admin
Systems | Test Approach | Activity | Owner | Dependencies
Peer Review WI | Creation of Policies with Partial / Live Status in Subscribe System. | Data Setup | Subscribe Team | Subscribe System needs to be integrated with Work View. Subscribe Team is responsible for the Data Setup.
 | Scheduled Batch Process to create the work item in Work View System. | Run Batch Job | Dev Team | The necessary support from Dev team for running the batch process to retrieve details from Subscribe.
 | Creation of work item when Partial Policy / Quote is created and Manual creation of Peer Review work item. Validation of automatically created work item after the Policy Processing. | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team. Work View user should be set up with the appropriate role to access the work item.
 | Process of work item actions involving Capture, Update, Index, Electronic Peer Review, Query to UW, Updating Front Sheet details. | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team. Work View user should be set up with the appropriate role to access the work item.
FAC Admin | Creation of Policy / Policy Subsequent Transaction with the FAC Alert in Subscribe System. | Data Setup | Subscribe Team | Subscribe System needs to be integrated with Work View. Subscribe Team is responsible for the Data Setup.
 | Validation of automatically created work item once after processing the Policy Feed which has records with FAC Alert. Manual Creation of FAC Alert work item. | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team. Work View user should be set up with the appropriate role to access the work item.
 | Process of work item actions involving Capture, Update, Index, Electronic Peer Review, Query to UW, Updating Front Sheet details. | Testing | SIT Team | Access for Work View system needs to be provided to SIT Team. Work View user should be set up with the appropriate role to access the work item.

## Slide 14
CGM Business Workflow - eEndorsement, Messaging & Rate Monitoring
Systems | Test Approach | Activity | Owner | Dependencies
Endorsement | Validation of the endorsement work item created once after receiving the WebCon message. | Testing | SIT Team | WebCon Integration should be established with Work View System. Work View user should have required privilege to access the work item.
 | Process of work item actions involving Capture, Index, Re-assign, Respond to message, Update. | Testing | SIT Team | Work View user should have required privilege to access the work item.
General Query Workflow | Creation of Query from Policy/Submission file manually by the user | Testing | SIT Team | WebCon Integration should be established with Work View System. Work View user should have required privilege to access the work item.
 | Process of Query actions involving raise Query, Send Query, Review, Re-assign, Respond to Message. | Testing | SIT Team | Work View user should have required privilege to access the work item.
Rate Monitoring | Creation of work item by Automatic Batch process and Manual creation of Rate Monitoring work item. | Testing | SIT Team | Subscribe System needs to be integrated with Work View . Work View user should have required privilege to access the work item.
 | Process of work item actions involving work item Capture, Update, Index, Query, ‘Price monitoring’ data import, Calculate Rate Change, ‘Benchmarking information’ import to UW, Provide Sign-off, Reject. | Testing | SIT Team | Work View user should have required privilege to access the work item.

## Slide 15
CGM Business Workflow - Cover Holder
Systems | Test Approach | Activity | Owner | Dependencies
Risk Registration WI | Creation and Validation of Risk Registration WI Ingesting a Scanned document Created as part of the indexing process Manually when creating a Submission | Testing | SIT Team | Subscribe System needs to be integrated with Work View. Work View user should have required privilege to access the work item.
 | Work Item validation in WorkView UI and Indexing with Policy File interfaced from Subscribe System Creation of New Submission File in WorkView Indexing of Risk Registration Work Item with Submission File that is created | Testing | SIT Team | Work View user should have required privilege to access the work item. WorkView User should have appropriate access to create a New Submission File
 | Process of work item actions involving Pend/Un-pend, Re-assign, Registration Complete | Testing | SIT Team | Work View user should have required privilege to access the work item.
Scan to Xchanging WI | Placing of Documents in WebCon that need to be routed to Xchanging | Data Set Up | WebCon | WebCon Integration should be established with Work View System for ACORD message transactions. Work View user should have required privilege to access the work item.
 | Data Cap scanning by selecting ‘Scan to Xchanging’ option | Data Cap Scanning | SIT Team | Access to Scanner Machine which is configured with Data Cap UI.
 | Validation and Indexing of work item that are created . | Testing | SIT Team | Work View user should have required privilege to access the work item.

## Slide 16
CGM Business Workflow - Cover Holder
Systems | Test Approach | Activity | Owner | Dependencies
Cover Holder | Creation of work item manually from a Policy/Submission file | Testing | SIT Team | Subscribe System needs to be integrated with Work View. Work View user should have required privilege to access the work item.
 | This work item is where the user will coordinate the individual work items that need to be created and completed for the process Indexing of Risk Registration Work Item with Submission File that is created | Testing | SIT Team | Work View user should have required privilege to access the work item. WorkView User should have appropriate access to create a New Submission File
 | Process of work item actions involving Send Query, Send Work item, Send for Approval, Pass/Fail, Re-assign, Complete | Testing | SIT Team | Work View user should have required privilege to access the work item.

## Slide 17
Requirements
Analysis
Design
Construction
Testing
User Acceptance
Category | Component | Functionalities
Core | Ingestion | Drag & Drop
 |  | Email Broker
 |  | DataCap Scanning
 |  | Upload
 |  | Save and Send
 | XPression | Barcode Generation
 |  | Document Generation
 | Daeja Viewer | Viewer Configuration
 |  | Bookmark
 |  | Split/Merge
Core Extended | Security | PIP / PAP / PDP
 |  | Single Sign On
 |  | System Access
 |  | User Preferences
 | VEGA UI | View Notification
 |  | Diary
 |  | Flags & Milestones
 |  | Alerts & Notes
 |  | Search Templates
 |  | Document Panel
 |  | Perform Document Indexing
 |  | Print Export
CGM Component Matrix
Category | Component | Functionalities
CGM Workflow | Business Transactions | Exception Authorisation
 |  | Risk Registration
 |  | Rate Monitoring
 |  | eEndorsement
 |  | Peer Review
 |  | Cover Holder
 |  | QC Validation
 |  | Contract Certainty
 |  | Scan to Xchanging
 |  | Fac Admin
 |  | General Query
Interfaces | Subscribe | Open File / View File
 |  | Update File
 | WebCon | Message Validation

## Slide 18: CGM Test Scope, Test Process & Deliverables
CHUBB Global Market

## Slide 19
Requirements
Analysis
Design
Construction
Testing
User Acceptance
CGM Test Scope
Pre-QA Testing
Sanity / Smoke
  Static Validation of Requirements, Use Cases, Configuration Sheets, Document Templates, etc
  Validation of build before the actual test execution starts to verify the working of basic happy path flow.
System Integration Testing
  Integration testing to cover the E2E workflow between all the integrated components involving Vega Unity, FileNet, Ingestion, XPression, Subscribe, WebCon, etc.,
Performance Testing
  NFR Identification & Gathering
  Performance Environment Setup & Tools Feasibility
  Performance Monitoring & Reporting

## Slide 20
Requirements
Analysis
Design
Construction
Testing
User Acceptance
CGM Quality Gate - Pass % and Open Defects from Cycle
Test Cases Execution: Pass % |  | 
Build Plan | Cycle 1 | Cycle 2
Build 1A - Test Execution | 65% | 80%
Build 1B - Test Execution | 65% | 85%
End to End - Test Execution | 85% | 90%
Signoff Criteria from SIT to UAT:
0 P1 & P2 Defects
Successful Smoke Test in UAT with all Integrated components
End to End Pass % > 90
Need to achieve the above mentioned test execution pass % in order to start with next test execution cycles,

## Slide 21
Requirements
Analysis
Design
Construction
Testing
User Acceptance
Functional Test Process & Deliverables
Test Initiation/ Approach
Requirements Analysis & Test Planning
Test Design
Test Execution
Unified Test Approach
Baseline Estimates
RTM
Reviewed Test Scenarios
Test Data
Test Cases
Requirements
Analysis
Design
Construction
Testing
User Acceptance
Test Closure
Implementation
Maintenance
Create Test Approach
Analyze requirements
Baseline Estimates
Requirement Ambiguity Clarification
Prepare Test Conditions/Scenario
Prepare Test Cases
Peer Review
Prepare Test Data
Prepare Requirements Traceability Matrix
Walkthrough scenarios with BA & Business
Collect Test Design Metrics
Check for Test Execution Readiness
Execute planned test cases
Log defects in QC & map it to associated test cases
Retest and track defects to closure
Provide support to UAT
Execute Regression
Signoff on ST & SIT
Prepare End of Test Summary Report
Provide signoff on UAT testing
Production Checkout
Conduct Release Retrospection
Identify reusable components and update test repository
Prepare production validation plan
Perform implementation dry run
Static Validation of Requirements
Prepare Execution Dashboard
Test Execution Report
Defect Logs
Business Readiness Dashboard
Test Summary Report
Release Retrospection
GO-NO GO Recommendations
QA Deliverables

## Slide 22
Requirements
Analysis
Design
Construction
Testing
User Acceptance
CGM Defect Management Process
‘New' Defects logged in the Defect Management Tool
Identify Defects through test execution Process
Review the defects [completeness]
Match requirement with expected results.
Log defects in the defect management tool HP ALM
Test Team
Triage the Defect [Need info, duplicate, New / missed requirement, processing issue].Reclassify defect to change control, if new requirement
Ensure defect holds all required information(Requirement reference, Application Screenshot)
Prioritize the defects- Reena
Assign to relevant development lead (Cognizant/Vega- Functionality)
Defect Assigned
Update the Development / Testing Team of Defect Status
Defect
Prevention Plan
Test Summary Report
Analyze and fix defects
Defect Review & Assignment
Defect Investigation, Fix & Unit Test
Update defect details; including resolution and root cause
List Level top 3 defect types
Root Cause Analysis of defects and update Defect Prevention Plan
Calculate Error Discovery rate and Defect Density
Calculate the number of defects based on Priority, status and Functionality
Calculate Quality of Fixes
Calculate Defect Aging
Defect
Coordinator (Sushma)
Dev Lead /
Development
QA ,
Dev Team
& Business Team(s)
QA lead
Process
Activities
Deliverables
Roles
Closed Defects
Retest Defect Fixes – With in 3 Days and execute the impacted test cases.
Test Team
Development Team
QA
Lead
Test
Team
Defect Metrics
Defect Triage/Assignment
Defect Trend Analysis &Prevention
Defect Identification
Retest and Closure
Defect Fixing
Defect
Coordinator
BA (Reena)
Team
Cognizant Dev Team
Env
BA
Vega Dev
Ingestion(L)
MI (L)
BizTalk(L)
xPression(L)
FileNet (L)
Daeja(L)
Corresponding
Team

## Slide 23
Requirements
Analysis
Design
Construction
Testing
User Acceptance
CGM Defect Process Workflow
Start
Execute Test Case/Scripts
Is Defect Found?
QA
QA
Pass Test Case/Script
Create New Defect
QA
QA
Yes
No
Open the defect & assign to Developer / BA
BA / DEV
QA
BA Assigned
Analyze the defect and Update Priority
(BA only)
Need More Info?
Is Defect Valid?
No
Is Defect Duplicate?
Yes
Is Defect Deferred?
No
BA / DEV
BA / DEV
BA / DEV
BA
DEV
Request info & re-assign the defect to QA
QA
Update requested information
QA
Open the defect & assign to Developer
Fix Post Prod?
Yes
Close the defect with reason as Deferred
Close the defect with reason as Duplicate
Assign defect to BA
Is Requirement Change ?
No
Request to validate Test case and/or Test data
BA / DEV
BA
QA
QA
QA
Closed
Initiate Change Control Process
Update root cause as Req. change and assign defect to QA
Close the defect with reason as Requirement Change
Test case and/or data invalid?
Yes
Is Reproducible
Yes
Reject Defect & Update Root Cause
Pass / Update Test Case/Script
QA
End
Close defect, update root cause and reason for closing
Closed
Fix the Defect & update the root cause
Defect is on hold for future build
Re-submit the defect and assign it to Developer
Is Re-test success?
Yes
Assign the fixed defect to QA
Retest the fixed defect
Close the defect & update reason for closing
No
If defect reoccurs
Dev
Dev
QA
QA
QA
QA
QA
QA
No
Yes
No
BA
BA
QA
QA
QA
QA
QA
Yes
Defect Triage
BA / DEV / QA
No
Yes
No
Rejected
No
Closed
Start / End
Pre-defined Activity
Activity
QA – Quality Analyst
BA – Business Analyst
Dev - Developer
Closed
Closed
QA Assigned
BA Assigned
IS Code
moved to
Test Envi
Move the code to UAT
Yes
No
Possible End Status
LEGEND
Defect Status
DEV Assigned
New
DEV Assigned
Fixed
Ready To Test
BA Assigned
Fixed
On Hold
QA Assigned
Resubmit

## Slide 24
Requirements
Analysis
Design
Construction
Testing
User Acceptance
Leveraging from ASPAC & NA…
Reusability of Test Cases from ASPAC & NA core components (Daeja Viewer, Ingestion, Send Email, Send Fax, Notes, Alerts, Notifications, XPression, etc.) to optimize the overall test design effort for CGM (Approx. 30% reusability of core components test artefacts)
Leveraging ASPAC/NA Core Business Knowledge & Expertise by involving the ASPAC/NA QA resources during CGM test design
Alignment of Quality Center Architecture to ensure maximum reusability,
Core: Reuse across regions without change;
Core Extended: Update the test cases based on the region wise business rules / file properties;
CGM: Business functionalities related to CGM;
Test Design
Test Execution
Prioritizing the test execution plan based on the business criticality of the components so that to execute high priority test cases at the earliest
Reusing the complete Test Data Setup prepared for ASPAC / NA components (Daeja Viewer, ICC, Upload, Drag & Drop, Send Fax, Send Email, etc) during NA test execution
Adopting the best practices & automated utilities developed in ASPAC / NA - Automated Daily Quality Dashboard, Automated ICC Audit Log Verifier, Dynamic Screen Capture Tool, Automated QC Utilities, etc.

## Slide 25
Appendix – Documents Referred
SL.No | Documents Referred | Version Number
1 | CGM_R1_Functional _Specification | V0.15
2 | ACEView CGM Workflow TDD | V1_6
3 | ApolloRefresh_CGM_Extended_Design | V1_3

## Slide 26
Appendix