## Slide 1: Work View R2 COG – ASPAC High Level Plan & Test Approach
CHUBB Overseas General Insurance
Version1.9

## Slide 2
Agenda
AGENDA
R2 COG Indicative Timelines Overview
R2 COG High Level Overview & Interface Test Approach
R2 COG Test Scope, Process & Deliverables
R2 COG Quality Gates & Defect Management Process

## Slide 3: R2 COG – ASPAC Indicative Timelines Overview
CHUBB Overseas General Insurance
Version1.9

## Slide 4
R2 COG ASPAC – Indicative Timelines, Assumptions/Dependencies & Risks/Issues
Assumptions/Dependencies :
SIT environment should be available by 6th June & UAT Environment should be available by 26th Sep to perform the Sanity testing. SIT Environment is expected to be available with the all the Interfaces(Meridian/ACC/OFAC/ACRS/System6/UWP/GenNext) and connected with Work View as per the schedule The high level timelines might change based on the change in the build plan (VEGA components/Interface) SIT test execution is planned to commence from 13th June 2016 and UAT test execution from 3rd Oct 2016 During Handshaking / End to End Testing, Support is required from Integrated System POCs SIT sign off will be given by end of September excluding UWP interface. SIT sign off including UWP will be shared by end of Oct
Risks/Issues | Key Dates | Ownerships
To share the Build Plan date for GenNext and OFAC sanction. The Delay in Build deployment would impact the UAT start | 15th April 2016 | Kevin Larison
Requirement Traceability Matrix between Functional Spec Document and Region specific requirement documents is required to proceed with the Test Design | 22nd April 2016 | Ollie Ferreira
The Business Process Flow diagram Between Interfaces and Work View is required to come up with End-to-End Business Scenarios | 22nd April 2016 | Kevin Larison/Ollie Ferreira
Field mapping between interface and Work View application to be shared | 29th April 2016 | Anton Savich/Integration team
Build Dates of VEGA components are to be shared or else it will impact SIT application testing | 15th April 2016 | Kevin Larison/Anton Savich
COG R2 Indicative Timelines | Apr-16 |  |  |  | May-16 |  |  |  |  | Jun-16 |  |  |  | Jul-16 |  |  |  | Aug-16 |  |  |  |  | Sep-16 |  |  |  | Oct-16 |  |  |  |  | Nov-16 |  |  |  | Dec-16 |  |  |  | Jan-17 |  |  |  | 
 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30
Requirements Analysis | Req Anal. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test Strategy & Planning | Test Strategy & Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test Design (Test Scenarios & Test Cases) |  |  | Test Scenarios & Test Cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
System Testing (Components) |  |  |  |  |  |  |  |  |  |  | Component details in slide 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Interface Testing excluding UWP |  |  |  |  |  |  |  |  |  |  | ACRS, System6, ACC, Meridian, OFAC Sanction, Gen Next |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Interface Testing - UWP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UWP SIT + E2E UWP and Meridian Casualty |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
End-to-End Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Components & Interface excluding UWP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
User Acceptance Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UAT without UWP |  |  | UAT with all interfaces |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SIT Env.
UAT Env.

## Slide 5
R2 COG ASPAC Interface Testing Timelines
Interface | Build Dates | TDC/TDF | LOB | Policy/Claim | Cycle 1 Date | Cycle 2 Date | Start Point (WorkView/Interface)
ACRS | 13th June 16 | TDF | A&H | Policy | 13/06/2016 | 11/07/2016 | ACRS
System 6 | 24th June 16 | TDF | A&H | Policy | 24/06/2016 | 18/07/2016 | System 6
Meridian | 01st July 16 | TDC | P&C and A&H | Both | NA | NA | Either way
ACC | 26th July 2016 | TDC | P&C and A&H | Claim | NA | NA | WorkView
UWP | 08th Sep 2016 | TDC | P&C | Policy | NA | NA | Either Way
OFAC Chubb Sactions | TBC | TDC | NA | NA | NA | NA | Either Way
GenNext | TBC | TDC | P&C | Policy | NA | NA | WorkView
- CHUBB
LEGENDS
- Cognizant (Testing team)
- Accenture
C1 - Cycle 1; C2 - Cycle 2;
TDC - Test Data Creation
TDF - Test Data Feed
ST - Smoke Test
COG R2 ASPAC Interfaces Indicative Timlines | May-16 |  |  |  | Jun-16 |  |  |  | Jul-16 |  |  |  | Aug-16 |  |  |  |  | Sep-16 |  |  |  | Oct-16 |  |  |  | 
 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31
ACRS |  |  |  |  | TDF | ST | C1 |  |  | C2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
System 6 |  |  |  |  |  | TDF | ST | C1 |  |  | C2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Meridian - Policy |  |  |  |  |  |  |  |  | ST | TDC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | C1 |  |  | C2 |  |  |  |  |  |  |  |  |  |  |  |  | 
Meridian - Claims |  |  |  |  |  |  |  |  |  | TDC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | C1 |  | C2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ACC |  |  |  |  |  |  |  |  |  |  |  | ST | TDC |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | C1 |  |  | C2 |  |  |  |  |  |  |  |  |  | 
UWP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ST | TDC |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C1 |  |  |  | C2 |  |  | 
OFAC Sactions | Build deployment date is yet to be confirmed/shared |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Gen Next | Build deployment date is yet to be confirmed/shared |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SIT Env.
UAT Env.

## Slide 6: R2 COG ASPAC Overview & Interface Test Approach
CHUBB Overseas General Insurance
Version1.9

## Slide 7
R2 COG ASPAC High Level Overview-Singapore
Send Email & Send Fax
Claims/UW Workflow
Work View –
Vega UI
Daeja Viewer
ASPAC
Interfaces
ACC
MS
Biz Talk
Work View Web Services
APP DB
File Net
Ingestion Components
ACC Web Services
RS6000/FTP server
Datacap
EmailICC FS
New UW
Portal
OFAC Sanction
ACRS
Meridian
System 6
Drag&Drop
WorkView Print
Upload
Save&Send
A
A
B
B
Data Communication
Doc Communication
LEGENDS
ICC File System
C
D
C
C
Web service
C
B
Data Btw Interfaces
FTP Window
D
GenNext
Doc Gen

## Slide 8
R2 COG ASPAC Interface Testing Timelines & Communication
  System 6 –A&H Master, Certificate Files (Child Policies) and related Documents would be sent to WorkView Via Batch Process.
  ACRS –A&H Master, Certificate Files (Child Policies) and related Documents would be sent to WorkView Via Batch Process
Communication(1 Way)
Communication(2 Way)
Interface System | Mode of Interaction | Changes in Interface (Yes/No) | Test Data Owner | Timelines |  |  |  | Dependency
 |  |  |  | Batch 1 Volume | Batch 1 Date | Batch 2 Volume | Batch 2 Date | 
ACRS | Scheduled Batch | No | ACRS Team | 300 | 13th Jun | 100 | 11th July | ACRS Team to provide the Policy Feed which contains Master and Its child policies BA to share the mapping document
System 6 | Scheduled Batch | No | System6 Team | 300 | 24th Jun | 100 | 18th July | Accenture Team to provide the Policy Feed which contains Master and Its child policies BA to share the mapping document
Interface System | Mode of Interaction | Changes in Interface (Yes/No) | Test Data Owner | Timelines |  |  |  | Dependency
 |  |  |  | Batch 1 Volume | Batch 1 Date | Batch 2 Volume | Batch 2 Date | 
ACC | Web services | Yes | ACC Team | N/A. The data feed is real time between ACC and WorkView. No batch job required |  |  |  | ACC Team to Key in New Claims and amend the claim in ACC or Accenture Team to provide necessary access to SIT team to set up data. BA to share the mapping document.
Meridian | Scheduled Batch/ APSYNC Job | No | SIT Team | N/A. The data feed is real time between Meridian and WorkView. |  |  |  | Access to be provided for SIT testing team to create Policy/Claim files. BA to share the mapping document.
UWP | Web services | Yes | SIT Team | N/A. The data feed is real time between UWP and WorkView. No batch job required |  |  |  | Access to be provided for SIT testing team to create Policy files. BA to share the mapping document
OFAC Sanction | RealTime/ Schedule Batch | No | CHUBB | N/A. The Insured creation will start from WorkView |  |  |  | Necessary access to be provided to SIT team to validate the Black Listed Insureds
Gen Next | Web service | Yes | MIDC team | N/A. The datacreation will start from WorkView |  |  |  | Necessary access to be provided to SIT team to validate the policy information

## Slide 9
R2 COG ASPAC Interface Testing Timelines & Communication(Contnd..)
Communication(2 Way)
  ACC – Claims created in ACC would be displayed in WorkView Via Web service. File Note( Note+ Document) created on ACC claims in WorkView will be sent back to ACC System.
  Meridian – Skeleton Policies created in Work View would be sent to Meridian System and Subsequent Policy/Claim Transaction in Meridian would be Synchronised with WorkView Via batch process
  UWP – Submission/Quote/ Policy and Related Documents would be sent , which creates Policy Case along with data in WorkView. And Orphan Task(Case) created in Workview will be updated in UWP. Both Process occurs Via Web Service.
  OFAC Sanction– OFAC check would be triggered when new insured gets created in WorkView and OFAC will set the Sanction Flag for the Insured in WorkView.
Communication Between Interfaces
Inter Connected Interfaces | Functionality To be verified | Dependency
Meridian WorkView UWP | Amend the Policies /Perform transactions on the policies in Meridian which are created from UWP Validate the changes in WorkView as the APSYNC would synchronize Meridian changes with WorkView system UWP needs to be updated by WorkView Web service | Functionality can be checked only if all related services are Up and Running
Detailed Time Lines and Test Data Requirement is enclosed below
  The changes in Interface System Field/ Architecture/Process will not be part of WorkView Integration Testing
  Web service/Document service related to the Source system is not considered for SIT testing
  The End-to-End Business Process flow, which is not linked to WorkView. E.g: Genius DPS-- >WorkView.
WorkView SIT Testing Out of Scope

## Slide 10
R2 COG ASPAC-Data Interfacing-Test Approach
Interface | Data/Document Communication | Communication Mode | Test Approach | Activity | Owner | Dependencies
ACC | Data Communication | ACC Work View | Claim Creation for Different LOBs in ACC System PBI Casualty Auto Marine Cargo Perform different claim transactions such as Reserve set Payment, Closing and Re-opening the claim | Data Creation | ACC /SIT Team | The ACC system needs to be integrated with Work View Via BizTalk & available for data creation Data creation part will be dependent on ACC team if access to ACC application is not granted to SIT team.
 |  |  | Claim Field validation in WorkView against ACC Fields. Indexing of related documents with the Claim file that are created. Creation of File Note in a document that are indexed with ACC file | Testing | SIT Team | Access for Work View / ACC needs to be provided to SIT Team for validation purpose. Web services should be Up and Running.
 |  | WorkView  ACC | Tasks/Document Taxonomy which are created on ACC claim would be sent to ACC along with Document File Note Validation of the same in ACC System | Testing | SIT Team | Access for Work View / ACC needs to be provided to SIT Team for validation purpose. Web services should be Up and Running.
 | Document Communication | WorkView  ACC | Creation of File Note for a Document which is linked with ACC Claim in WorkView and Validation of same in ACC System. Perform indexing/re-indexing on the document in which file note is created. | Testing | SIT Team | Access for Work View / ACC needs to be provided to SIT Team for validation purpose. Web services should be Up and Running.
 |  |  | Validation of File Note in ACC System Launch the documents in ACC Daeja Viewer that are created in ACC from WorkView Validate the document properties | Testing | SIT Team | Access for Work View / ACC needs to be provided to SIT Team for validation purpose. Web services should be Up and Running.
 |  | ACC  WorkView | ACC FTP service to extract the documents and place the same into the respective WorkView FTP service | Document Extraction | Accenture | WorkView ICC File System should be up and running
 |  |  | Validation of documents which are ingested into WorkView System once after the ICC File System process | Testing | SIT Team | SIT Team requires appropriate access to validate the document.

## Slide 11
R2 COG ASPAC-Data Interfacing-Test Approach
Interface | Data/Document Communication | Communication Mode | Test Approach | Activity | Owner | Dependencies
Meridian | Data Communication | WorkView  Meridian | Policy Registration in WorkView System for Different LOBs such as Casualty ,Auto, Marine Cargo, PBI. | Testing | SIT Team | WorkView System should be integrated with Meridian System. APSYNC Job needs to be Up and Running and also the BizTalk Service. SIT Team requires appropriate access to set up the Policy in WorkView.
 |  | Meridian  WorkView | Enriching the policies sent from WorkView in Meridian System. Expand the skeleton policy &perform different policy transactions such as Endorsement, cancelation and renewal etc. Claim set up in Meridian for the policies that are created Perform claim subsequent transaction like reserve set up , settling and re-opening the claim Perform Subsequent transactions on the policy that are created from UWP. | Data Set Up and Testing | SIT Team | WorkView System should be integrated with Meridian System. APSYNC Job needs to be Up and Running and also the BizTalk Service. SIT Team requires appropriate access to Meridian System to perform Policy &Claim actions
 |  |  | Field wise validation of policies and claims against the meridian files Status validation of Policy/claim files in Workview as and when the transaction is being performed in Meridian | Testing | SIT Team | WorkView System should be integrated with Meridian System. APSYNC Job needs to be Up and Running and also the BizTalk Service.
 | Document Communication | Meridian  WorkView | PBE Documents from Meridian System to be sent to the FTP location and ICC File System would direct them into work view. Invoice document from meridian would be sent to WorkView via Email Broker Validate whether the documents are ingested into respective claim/policy files in WorkView | Testing | SIT Team | WorkView System should be integrated with Meridian System. APSYNC Job and ICC File System service needs to be Up and Running

## Slide 12
R2 COG ASPAC-Data Interfacing-Test Approach
Interface | Data/Document Communication | Communication Mode | Test Approach | Activity | Owner | Dependencies
ACRS | Data Communication | ACRS  WorkView | Manually Placing the ACRS Policy feed into the Configured FTP path Policy and Certificate Field Validation in Work View against the data feed that are processed Indexing of related documents with the Claim file that are created. | Testing | SIT Team | Scheduled Batch needs to be Up and Running and also the BizTalk Service. ACRS team to provide the policy data feed
 | Document Communication | ACRS  WorkView | Extract the ACRS Policy Documents and Ingest the document into ACE View using Email Functionality Validate whether the documents are ingested into respective claim/policy files in WorkView | Document Ingestion | SIT Team | The ACRS Document Service to send the Document to configured to WorkView Email Boxes.
System 6 | Data Communication | System 6 WorkView | Manually Placing the System6 Policy feed into the Configured FTP path Policy and Certificate Field Validation in Work View against the data feed that are processed Indexing of related documents with the Claim file that are created. | Testing | SIT Team | Scheduled Batch needs to be Up and Running and also the BizTalk Service. System6 team to provide the policy data feed
 | Document Communication | Systen6  WorkView | Extract the System6 Policy Documents and Ingest the document into ACE View using FTP Window service Validate whether the documents are ingested into respective claim/policy files in WorkView | Document Ingestion | SIT Team | The System6 Document Service to send the Document to the FTP Window ICC File System service to be up and running

## Slide 13
R2 COG ASPAC-Data Interfacing-Test Approach
Interface | Data/Document Communication | Communication Mode | Test Approach | Activity | Owner | Dependencies
UWP | Data Communication | UWP WorkView | Set up New Business Policy in UWP with different status(Submission , quote and authorized policy). Creation Policy Subsequent Transaction such as Endorsement ,renewal, cancellation ,NTU, Decline and reinstate | Data Set Up | SIT Team | Work view should be integrated with UWP Via BizTalk Service. BizTalk Service should be active SIT Team needs to be provided with UWP System Access
 |  |  | Field Validation of New Business Policy Files in WorkView which are created from UWP System. Validation of the existing Policy upon the transaction changes in UWP System Validation of Policy Case in WorkView that are created upon Policy Status Change in UWP. Create Orphan Task in Work View System and also create skeleton policies in WorkView | Testing | SIT Team | Work view should be integrated with UWP Via BizTalk Service. BizTalk Service should be active SIT Team needs to be provided with UWP System Access
 |  | WorkView  UWP | Field Validation of skeleton policies and insureds that are created in work view is integrated to UWP | Testing | SIT Team | Work view should be integrated with UWP Via BizTalk Service. BizTalk Service should be active SIT Team needs to be provided with UWP System Access
 | Document Communication | UWP WorkView | Policy/Quote Document generated in UWP upon different transactions would be sent to WorkView via web services Validate whether the documents are ingested into respective claim/policy files in WorkView | Document Ingestion | SIT Team | WorkView needs to be integrated with UWP Document Service should be up and running

## Slide 14
R2 COG ASPAC-Data Interfacing-Test Approach
Interface | Data/Document Communication | Communication Mode | Test Approach | Activity | Owner | Dependencies
Chubb OFAC Sanction | Data Communication | WorkView OFAC | Creation of New Policy with the existing Insured/Policy Holder in which OFAC sanction check is enabled in WorkView | Data Set Up | SIT Team | WorkView System should be integrated with D&B System. Scheduled Batch needs to be Up and Running and also the BizTalk Service. The Account used for Policy creation should have OFAC check is enabled
 |  | OFAC WorkView | Validation of the OFAC Flag is set as and when the WorkView interacts with D&B System | Testing | SIT Team | WorkView System should be integrated with D&B System. Scheduled Batch needs to be Up and Running and also the BizTalk Service.

## Slide 15
R2 COG ASPAC Test Data Requirement
Interfaces | Transactions | Owner | No. of Files (Cycle 1) | No. of Files (Cycle 2) | Remarks
ACC | Creation of new Claim and on different LOBs PBI Casualty Auto etc. Amend the claim by performing various transactions like Reserve Set , Payment, Recovery &Settlement Claim with Different status like Closed , Declined and Re-opened | ACC/Wok View SIT team | 300 | 100 | Required WorkView Integrated with ACC. ACC team to provide the Files with requested data specification / required access to ACC System to perform the necessary transactions
Meridian | Policy Files on different LOBs with following criteria Policies on various LOBs like Casualty & Property New Business Policy with New Insured/Existing Insured Expanding and authorizing the skeleton policy created from WorkView Policy Subsequent Transactions like Renewal, Endorsement ,Cancellation etc. Amend or perform different transaction on the policies that are created from UWP source system | WorkView SIT Team | 300 | 100 | Required WorkView Integrated with Meridian Environment. SIT team is to be provided with appropriate access to set up the data
 | Creation of new Claim and on different LOBs PBI Casualty Fire Auto etc. Amend the claim by performing various transactions like Reserve Set , Payment, Recovery &Settlement Claim with Different status like Closed , Declined and Re-opened | WorkView SIT Team | 300 | 100 | Required WorkView Integrated with Meridian Environment. SIT team is to be provided with appropriate access to set up the data

## Slide 16
R2 COG ASPAC Test Data Requirement-Contd..
Interfaces | Transactions | Owner | No. of Files (Cycle 1) | No. of Files (Cycle 2) | Remarks
ACRS | Creation of New Business Policy with different status like In progress, Quoted, Bound and Authorized. Subsequent policy transaction on existing New Business Policy like Endorsement ,Renewal , Cancellation etc. | ACRS team | 300 | 100 | Required WorkView Integrated with ACRS System. ACRS team to provide the Files with requested data specification / required access to ACRS System to perform the necessary transactions
System 6 | Creation of A&H Certificate Mater Policies with various status like In progress, Quoted, Bound and Authorized. Subsequent policy transaction on existing New Business Policy like Endorsement ,Renewal , Cancellation etc. | System6 Team | 300 | 100 | Required WorkView Integrated with System6. System6 team to provide the Files with requested data specification / required access to System6 System to perform the necessary transactions.
UWP | Policy Files on different LOBs with following criteria Policies on Property and Casualty LOB New Business Policy with New Insured/Existing Insured Expanding and authorizing the skeleton policy created from WorkView Policy Subsequent Transactions like Renewal, Endorsement ,Cancellation etc. | WorkView SIT Team | 300 | 100 | Required WorkView Integrated with UWP Environment. SIT team is to be provided with appropriate access to set up the data
OFAC Sanction | Insured List which are blacklisted for OFAC Sanction check | TBD | 50 | 20 | Required WorkView to be Integrated with Chubb/D&B system.

## Slide 17
Requirements
Analysis
Design
Construction
Testing
User Acceptance
R2 COG ASPAC In Scope Component Matrix.
Category | Component | Functionalities
COG ASPAC Interfaces | Interface Integration | ACC Integration
 |  | Meridian Integration
 |  | ACRS Integration
 |  | System6 Integration
 |  | UWP Integration
 |  | OFAC Sanction
 |  | Gen Next

## Slide 18: R2 COG ASAPC Test Scope, Test Process & Test Deliverables
CHUBB Overseas General Insurance
Version1.9

## Slide 19
Requirements
Analysis
Design
Construction
Testing
User Acceptance
R2 COG ASPAC Test Scope
Pre-QA Testing
Sanity / Smoke
  Static Validation of Requirements, Use Cases, Configuration Sheets, Document Templates, etc
  Validation of build before the actual test execution starts to verify the working of basic happy path flow.
System Testing
System Integration Testing
  Individual Component Level Testing
  Integration testing to cover the E2E workflow between all the integrated components involving Vega Unity, FileNet, Ingestion, XPression, Interface Systems,etc.,
Performance Testing
  NFR Identification & Gathering
  Performance Environment Setup & Tools Feasibility
  Performance Monitoring & Reporting
Automation Testing
  Identifying the components which can be automated
  Identifying the common component which can be reused from earlier releases

## Slide 20
Requirements
Analysis
Design
Construction
Testing
User Acceptance
R2 COG ASPAC AUTOMATION COVERAGE
CORE SCENARIOS AUTOMATED
Workbasket Actions: Pend, Unpend, Re-assign, Priority, Close, Unlock, Bulk Actions
Document Actions: Copy, Move, Link, Delete, Filter, Hide, Unhide
Ingestion: Email Broker / Scanning / Upload
Notes & Alerts
Security & System Access
User Preferences
Core Scenarios Automated will be reused across Regions with minor modifications.
REGIONAL SCENARIOS AUTOMATED
Out of scope for Automation
Daeja Viewer - Java Applet based Component (Document Viewer)
Drag & Drop - Windows based Component
Send Email & Fax - Windows based Component (Outlook)
Apollo Print - Windows based Component
Document Content Verification
X Pression: Barcode & Doc Gen
Flags, Milestones, Correspondents
Work Flow, Indexing, Search Templates
ASPAC:
R2 Specific Scenarios to be automated:
Customer Interaction
Complaints
BIRI
Policy/Claims/Accounts/Brokers UI Validation
In-Scope for Automation

## Slide 21
SIT - Functional Test Process & Deliverables
Test Planning
Test Design
Test Execution
Test Strategy
Test Initiation
Create Test Strategy
Participate in Requirements Walkthrough
Analyze requirements
Baseline Estimates
Requirement Ambiguity Clarification
Static Validation of Requirements
Prepare Test Conditions/Scenarios
Prepare Test Cases
Peer Review
Prepare Test Data
Walkthrough scenarios with BA
Collect Test Design Metrics
Check for Test Execution Readiness
Execute planned test cases
Log defects in QC and map it to associated test cases
Retest and track defects to closure
Prepare Execution Dashboard
Provide support to UAT
Execute Regression
Signoff on ST & SIT
Prepare End of Test Summary Report
Provide signoff on SIT
Conduct Release Retrospection
SIT / QA Deliverables
SALIENT FEATURES OF SIT PROCESS:
Test Coverage for all the Requirements.
  Requirement Traceability Matrix provided - All the requirements will be mapped to the test cases / defects and same will be established in QC.
  Test Scenarios are reviewed with IT BA and will also be available in QC for business team to refer.
Quality Gates established through stringent Entry and Exit Criteria for,
  Each Phase of STLC (Refer Subsequent Slides)
Testing focusses on both Upstream and Downstream activities, positively influencing Quality
Test Strategy (Reviewed and Signed off)
Reviewed Test Scenarios
Test Data
Test Cases
Test Execution Report
Defect Logs
Business Readiness Report
Test Summary Report
Release Retrospection
GO-NO-GO Recommendations
RTM (Requirements traceability matrix)
Test Closure

## Slide 22
SIT - Test Coverage - What is being covered?
Test Types | Test Coverage
Functional Test (Initial Cycles) -Component Level | UI Validation: Field Level Validation as per Configuration Sheet (Length, Data Type, Mandatory, Read/Write, etc.,) Error / Warning / Confirmation / Tool Tip Message Validation Region / Language Specific Validation (Data, Currency, etc.,) Core Functional Testing (Positive / Negative Workflow) Business Rules Testing User Roles / Privileges Testing Document Validation Exception Handling Validation Different Combination of Data Testing Browser Compatibility (Different IE Version and Java Versions) Different OS Versions.
Interface Testing | Validation of data / document flows between data interfaces & Work View Validation of data / document flows between interfaces Web Services Validation between interfaces Batch Validations
End to End Testing | Validation of End to End Business Process Flows Business Continuity Testing
MI Testing (Reports) - ETL Testing | ETL Testing Data Mapping Testing Backend Validation Testing Data Quality / Duplication Testing Data Transformation Logic Testing
Regression Testing | Automated Validation of Core Critical Functionalities after each build deployment / defect fixes
Projects Documents referred for Test Design - To provide complete test coverage
Requirement Catalogue
Use Case Document
Functional Specification
Configuration Sheet
TDD / SAS
INPUT
Test Scenario
Test Cases
Clarification Tracker
OUTPUT
SIT Test Coverage Checklist:
High Level Test Scripts: R2 COG
Functional Testing : 5900
Interface Testing : 2950
End to End Testing : 1250
Regression Testing : 1500
ETL / MI Report : TBD

## Slide 23
SIT - Test coverage - Example of Test cases and Coverage
Requirements
1. The ability to create a Policy File in WorkView
Req No 707
Policy FS Doc –2.3.2
Config. Doc
Test Case - Policy File Creation
Test Case Objective
To Verify whether the policy file created in Genius is getting updated in WorkView
FS-Document Name | FS Module No | Test Case Description | Pre-Condition | Step # | Steps | Expected Result
Policy Functional Spec | 2.3.2 | To verify whether the policy file is created in WorkView once the user is set up a new policy in Genius | 1. User should have access to login to WorkView. 2. New Business policy should be created in Genius System 3.APSYNC job should be up and running in every 5 mins | 1 | Login to WorkView with valid credential. | User should successfully logins to WorkView system and navigate to home page
 |  |  |  | 2 | Select the Policy Search Template | Policy Search template should be displayed with the search criteria
 |  |  |  | 3 | Fill the policy number field with special characters and Hit Search | Error Message should be displayed as the format is not recognized
 |  |  |  | 4 | Fill the policy number field with the policy number generated in Genius and Hit Search | Search result should be displayed by fetching the following fields with values 1.Policy Number 2.Policy Start 3.Account Name 4.Insured ID 5.Policy Insured 6.Master Policy No 7.Line of Business Group 8.Line of Business 9.Product 10.Field Office
 |  |  |  | 5 | Validate the field values against the Genius field values | The field values should be same as the values entered in Genius System
Interface Testing
Batch Validation
GUI Validation
Field Validation

## Slide 24: R2 COG ASAPC Quality Gates & Defect Management Process
CHUBB Overseas General Insurance
Version1.9

## Slide 25
Ensuring Quality Through Quality Gates
Phase wise Entry & Exit Criteria
Test Cases / Data
Reviewed
Signed-off
Test Plan/ Scenarios
Reviewed
Signed-off
Post-Production Testing and Support
Test Metrics
Test Summary Report
Test Closure
SIT test results sign-off,
UAT test results sign off
Performance test results sign off
Requirements
Reviewed
Signed-Off
Test coverage
Defect Severity
Test results signed-off
Test Coverage
Regression Coverage
Test Effectiveness
Defect Leakage
Test results signed-off
Code sanity tested
QA Environment Signed-Off
System Testing Signed-Off
Low priority defects moved to next stage
Integration of Application Under Test with other systems completed
Code Sanity Tested
QA environment Signed-Off
Signed-Off Design Documents
Unit Testing Signed-Off
Open Issues logged in QC
Requirements
Test Plan & Test Scenarios
Test Cases & Test Data
System Testing
System Integrated
Regression
Testing
Performance Testing
UAT
Design
Build
Go Live!
System Stage
System-Integration Stage
Test Execution Phase
Test Design Phase
Test Cases Execution: Pass % |  | 
Build Plan | Cycle 1 | Cycle 2
System Test Execution | 65% | 80%
Interface Test Execution | 65% | 85%
End to End - Test Execution | 85% | 90%
Regression Testing | 93% | 95%
Need to achieve the test execution pass % mentioned in the table in order to start with next test execution cycles,
Need to achieve Zero S1 & S2 defects to start with End to End Testing.
Need to achieve Zero P1 & P2 defects to start with Regression Testing.
Need to achieve Zero S1, S2, P1 & P2 defects to start with UAT Testing.

## Slide 26
Requirements
Analysis
Design
Construction
Testing
User Acceptance
R2 COG ASPAC Defect Management Process
‘New' Defects logged in the Defect Management Tool
Identify Defects through test execution Process
Review the defects [completeness]
Match requirement with expected results.
Log defects in the defect management tool HP ALM
Test Team
Triage the Defect [Need info, duplicate, New / missed requirement, processing issue].Reclassify defect to change control, if new requirement
Ensure defect holds all required information(Requirement reference, Application Screenshot)
Prioritize the defects- Alex
Assign to relevant development lead (Cognizant/Vega- Functionality)
Defect Assigned
Update the Development / Testing Team of Defect Status
Defect
Prevention Plan
Test Summary Report
Analyze and fix defects
Defect Review & Assignment
Defect Investigation, Fix & Unit Test
Update defect details; including resolution and root cause
List Level top 3 defect types
Root Cause Analysis of defects and update Defect Prevention Plan
Calculate Error Discovery rate and Defect Density
Calculate the number of defects based on Priority, status and Functionality
Calculate Quality of Fixes
Calculate Defect Aging
Defect
Coordinator (Alex)
Dev Lead /
Development
QA ,
Dev Team
& Business Team(s)
QA lead
Process
Activities
Deliverables
Roles
Closed Defects
Retest Defect Fixes – With in 3 Days and execute the impacted test cases.
Test Team
Development Team
QA
Lead
Test
Team
Defect Metrics
Defect Triage/Assignment
Defect Trend Analysis &Prevention
Defect Identification
Retest and Closure
Defect Fixing
Defect
Coordinator
BA Team
Cognizant Dev Team
Env
BA
Vega Dev
Ingestion(L)
MI (L)
BizTalk(L)
xPression(L)
FileNet (L)
Daeja(L)
Corresponding
Team

## Slide 27
Requirements
Analysis
Design
Construction
Testing
User Acceptance
R2 COG ASPAC Defect Process Workflow
Start
Execute Test Case/Scripts
Is Defect Found?
QA
QA
Pass Test Case/Script
Create New Defect
QA
QA
Yes
No
Open the defect & assign to Developer / BA
BA / DEV
QA
BA Assigned
Analyze the defect and Update Priority
(BA only)
Need More Info?
Is Defect Valid?
No
Is Defect Duplicate?
Yes
Is Defect Deferred?
No
BA / DEV
BA / DEV
BA / DEV
BA
DEV
Request info & re-assign the defect to QA
QA
Update requested information
QA
Open the defect & assign to Developer
Fix Post Prod?
Yes
Close the defect with reason as Deferred
Close the defect with reason as Duplicate
Assign defect to BA
Is Requirement Change ?
No
Request to validate Test case and/or Test data
BA / DEV
BA
QA
QA
QA
Closed
Initiate Change Control Process
Update root cause as Req. change and assign defect to QA
Close the defect with reason as Requirement Change
Test case and/or data invalid?
Yes
Is Reproducible
Yes
Reject Defect & Update Root Cause
Pass / Update Test Case/Script
QA
End
Close defect, update root cause and reason for closing
Closed
Fix the Defect & update the root cause
Defect is on hold for future build
Re-submit the defect and assign it to Developer
Is Re-test success?
Yes
Assign the fixed defect to QA
Retest the fixed defect
Close the defect & update reason for closing
No
If defect reoccurs
Dev
Dev
QA
QA
QA
QA
QA
QA
No
Yes
No
BA
BA
QA
QA
QA
QA
QA
Yes
Defect Triage
BA / DEV / QA
No
Yes
No
Rejected
No
Closed
Start / End
Pre-defined Activity
Activity
QA – Quality Analyst
BA – Business Analyst
Dev - Developer
Closed
Closed
QA Assigned
BA Assigned
IS Code
moved to
Test Envi
Move the code to UAT
Yes
No
Possible End Status
LEGEND
Defect Status
DEV Assigned
New
DEV Assigned
Fixed
Ready To Test
BA Assigned
Fixed
On Hold
QA Assigned
Resubmit

## Slide 28
Requirements
Analysis
Design
Construction
Testing
User Acceptance
R2 COG - Leveraging from R1 ASPAC & NA…
Reusability of Test Cases from ASPAC & NA core components (Daeja Viewer, Ingestion, Send Email, Send Fax, Notes, Alerts, Notifications, XPression, etc.) to optimize the overall test design effort for OGI (Approx. 30% reusability of core components test artefacts)
Leveraging ASPAC/NA Core Business Knowledge & Expertise by involving the ASPAC/NA QA resources during OGI test design
Alignment of Quality Center Architecture to ensure maximum reusability,
Core: Reuse across regions without change;
Core Extended: Update the test cases based on the region wise business rules / file properties;
R2 COG : Business functionalities related to COG
Test Design
Test Execution
Prioritizing the test execution plan based on the business criticality of the components so that to execute high priority test cases at the earliest
Reusing the complete Test Data Setup prepared for ASPAC / NA components (Daeja Viewer, ICC, Upload, Drag & Drop, Send Fax, Send Email, etc) during NA test execution
Adopting the best practices & automated utilities developed in ASPAC / NA - Automated Daily Quality Dashboard, Automated ICC Audit Log Verifier, Dynamic Screen Capture Tool, Automated QC Utilities, etc.

## Slide 29
Appendix – Documents Referred
SL.No | Documents Referred | SharePoint Path
1 | Functional Requirements | http://europespace.acegroup.com/sites/AR_AOGRel3_Project/SitePages/Home.aspx?RootFolder=%2Fsites%2FAR%5FAOGRel3%5FProject%2FShared%20Documents%2F03%5FFunctional%5FDesign%2F07%20Functional%20Requirements&FolderCTID=0x012000A94F981F8FF08D40A56C72D5EAD2B984&View={53B4DA14-BE86-4765-BF10-40864446FE75}
2 | Claim Functional Spec | http://europespace.acegroup.com/sites/AR_AOGRel3_Project/SitePages/Home.aspx?RootFolder=%2Fsites%2FAR%5FAOGRel3%5FProject%2FShared%20Documents%2F03%5FFunctional%5FDesign%2F03%20Claims&FolderCTID=0x012000A94F981F8FF08D40A56C72D5EAD2B984&View={53B4DA14-BE86-4765-BF10-40864446FE75
3 | Customer Interaction spec document | http://europespace.acegroup.com/sites/AR_AOGRel3_Project/SitePages/Home.aspx?RootFolder=%2Fsites%2FAR%5FAOGRel3%5FProject%2FShared%20Documents%2F03%5FFunctional%5FDesign%2F05%20Customer%20Interaction&FolderCTID=0x012000A94F981F8FF08D40A56C72D5EAD2B984&View={53B4DA14-BE86-4765-BF10-40864446FE75}
4 | Complaints Functional Spec | http://europespace.acegroup.com/sites/AR_AOGRel3_Project/SitePages/Home.aspx?RootFolder=%2Fsites%2FAR%5FAOGRel3%5FProject%2FShared%20Documents%2F03%5FFunctional%5FDesign%2F06%20Complaints&FolderCTID=0x012000A94F981F8FF08D40A56C72D5EAD2B984&View={53B4DA14-BE86-4765-BF10-40864446FE75}
5 | Interfaces Link | https://officespace.ace-ina.com/s/Apollo2Symposium/General/Forms/AllItems.aspx?RootFolder=%2Fs%2FApollo2Symposium%2FGeneral%2FApollo%20Refresh%20Program%2F07%5FRelease%5F2%2F12%5FInterface%5FAnalysis&FolderCTID=0x012000B7F9EC70C9752B4DA37DF18AA4F04B81&View=%7B63698F83%2DC9C8%2D44F4%2DA5E9%2D560C9C24594E%7D