## Slide 1: Work View Automation Report
Feb 2017
Version 0.1

## Slide 2
Cognizant QA Governance Summary - Sep 2016
HIGHLIGHTS
Release Updates:
  UW Portal August Release deployed successfully in Production with 9 CRs, 52 Warranty Incidents and for the Country Rollout - LATAM Panama CUP, APAC NZ CUP. SIT team has identified ~426 defects in SIT and production defect leakage is 0.23%.
  UW Portal September Release deployed successfully in Production with 7 CRs, Panama Casualty, 3 APAC country technical live & UKI rebranded quote letter.
  WorkView CGM UAT: 7 business workflows have been delivered to UAT execution and the remaining 3 workflows (eEndorsement, Scan to xChanging, Fac Admin) are planned to deliver by 17th Oct 2016. SIT team has identified ~1243 defects in SIT and there is no functional defect leakage into UAT.
  TTP Mexico - First LATAM region rollout for TTP is successfully delivered into production with no major issues in production.
  AOL September Release (UK/IE) : 2 Maintenance Incidents which were reported on July 2016,has been fixed and deployed into production.
CHALLENGES
Process Improvements:
  UW Portal Regression Cycle is reduced to 3.5 days from the initial 5 days through parallel execution & test script optimization
  WorkView : Implemented Automated Test Data Creation Utility for R2 COG Interfaces which will reduced the test data creation effort by 85%.
  Implementing End to End Quality Dashboard which will provide Single View of Quality across all the phase of SDLC - Requirements, Design, Build, SIT and UAT.
  UW Portal SIT: Delay in Completion of October Release SIT by 1 week due to High Code Quality Issues (~933 SIT Defects) and Environment Downtime (~682 person hours)
  WorkView R2 COG: Interface Data Mapping documents are yet to be baseline and Requirements for UW Portal, MMB, ACE Online interfaces are not available for test design. Working with BA to get the base-lined artefacts.
OTHERS
  Geethanjali Seenu, Test Manager has been on-boarded for Chubb Integration Testing.
  Pradeep Padmanaban, Test Manager has been on-boarded for UW Portal Programme Testing.
  Rajaraman S, Tester visa has been initiated for TTP programme and planning to onboard by Oct 1st week

## Slide 3
Cognizant QA Governance Summary - Sep 2016
HIGHLIGHTS
Foot Prints of 2016:
  Work View NA Test Regression
  Interface Test Data Automation for CGM (Subscribe and WebCon)
CHALLENGES
Process Improvements:
  UW Portal Regression Cycle is reduced to 3.5 days from the initial 5 days through parallel execution & test script optimization
  WorkView : Implemented Automated Test Data Creation Utility for R2 COG Interfaces which will reduced the test data creation effort by 85%.
  Implementing End to End Quality Dashboard which will provide Single View of Quality across all the phase of SDLC - Requirements, Design, Build, SIT and UAT.
  UW Portal SIT: Delay in Completion of October Release SIT by 1 week due to High Code Quality Issues (~933 SIT Defects) and Environment Downtime (~682 person hours)
  WorkView R2 COG: Interface Data Mapping documents are yet to be baseline and Requirements for UW Portal, MMB, ACE Online interfaces are not available for test design. Working with BA to get the base-lined artefacts.
OTHERS
  Geethanjali Seenu, Test Manager has been on-boarded for Chubb Integration Testing.
  Pradeep Padmanaban, Test Manager has been on-boarded for UW Portal Programme Testing.
  Rajaraman S, Tester visa has been initiated for TTP programme and planning to onboard by Oct 1st week

## Slide 4
Defects Reported (SIT)* | Nos. |  |  | 
Defect Rejection (SIT)* | % |  |  | 
Error Discovery Rate* | Rate |  |  | 
Quality of Fix | % |  |  | 
Defect Aging (P1 & P2) | Days |  |  | 
Defect Leakage (UAT)* | % |  |  | 
Overall Schedule Variance* | % |  |  | 
Build Rejection | Nos. |  |  | 
Environment Outage Hours | Hr |  |  | 
Automation Execution Productivity* | Nos. |  |  | 
Test Effectiveness* | % |  |  | 
Test Execution Coverage* | % |  |  | 
Regression Automation* | % |  |  | 
Reg. Automation Reusability* | % |  |  | 
Automation Preparation Productivity* | Nos. |  |  | 
Test Design Coverage* | % |  |  | 
Test Design Reusability* | % |  |  | 
Total Test Case Count* | Nos. |  |  | 
WorkView QA Score Card (Until Sep 2016)
Test Design Metrics
Test Execution Metrics
Quality Metrics
16
100%
NA
2497
13
98.17%
100%
80%
1379
1.83%
77.82%
10
478 Hr
0%
NA
0.55
Comparison of Testing Metrics with Different Regions
3
Note:* Indicates testing metrics - Indicates the performance of testing team
10
80%
23%
6175
10
80%
30%
4275
15
98.07%
100%
82%
24%
17
100%
92.34%
80%
38%
2596
1.93%
76.31%
15
400 Hr
1.2%
0.42
12
1232
0%
71.24%
19
858 Hr
2%
0.31
3
COG R2 LATAM
COG R2 EMEA
COG R2 APAC
Unit
Testing Delivery Measures
0.28%
0.46%
0%
Note:** CGM, R2 COG - Ongoing projects

## Slide 5
Cognizant Testing - Observations & Action Items
Metrics | Program | Observations | Action Taken | Owner
Quality of Fix | UW Portal | The QoF is consistently very low (~70%) across all the rollouts which can be improved to 85% to reduce SIT execution. | Mandated development team to track Unit Test logs in QC. | Dev Team
 |  |  | Mandate Impact Analysis for defect fix and prepare Impact Analysis document in agreement with other stakeholder | Dev Team
 | WorkView - CGM | The CGM QoF is considerably very low (~71%) comparing other releases. | Initiated to publish QoF tracker after every build and mandated Unit Testing in DEV environment. | QA / Dev Team
Error Discovery Rate | UW Portal | The EDR is consistently very higher (~1) than nominal benchmark value (0.3 - 0.4) across all the rollouts. | Planned to implement Handshake Testing between technology track ((Ex. BizTalk, FileNet, .NET, etc.) in Dev Env. | Dev Team
 | WorkView | The EDR is reducing from 0.5 to 0.3 over release to release which indicates the improvement in Code Quality. | No Action Required | NA
Requirement Stability | UW Portal | Absence of base-lined requirements in start of the project leads to multiple change requests in the later stages of SIT & UAT. | Initiated discussions with Chubb BA’s to get the base-lined requirements in prior the SIT test design phase. | QA / BA Team
 | WorkView - R2 COG | Interface Data Mapping documents are yet to be baseline and Requirements for UW Portal, MMB, ACE Online interfaces not available |  | 
Regression Automation % | UW Portal | Improve the Regression Script Efficiency & Parallel Execution (Multiple VDI / Brower's) to reduce the SIT regression cycle time. | Feasibility Study is in progress to perform parallel execution in multiple browsers. Initiated additional VDI requests to Chubb to perform parallel regression execution. | QA / Chubb
Production Leakage | UW Portal | 1 Production leakage related to Doc Gen in Aug release and 1 Production leakage related to Agent in Sept release which indicates the requirement of additional test case to be added in regression suite. | Additional Doc Gen and Agent test cases added in regression suite to avoid production leakage | QA Team
Environment Availability | UW Portal | The average environment unavailability is considerably high across all the rollouts. | Initiated discussions with environment team to have planned environment outage tracker to SIT team for better test execution plan. | QA / Dev / Env Team
 | WorkView - R2 COG | The environment unavailability (858 PH) impacted the SIT completion date by 6 weeks. |  | 

## Slide 6
Key Improvement Levers Implemented - Sep 2016
Test Design & Data
Requirements
  WorkView:
  Implemented Shift Left Strategy for Work View R2 COG and we have identified 30 defects via Requirements Static Testing & 28 defects via SOA Testing.
  WorkView:
  Implemented Automated Test Data Creation Utility for R2 COG Interfaces (Genius, Meridian, SIS) which will reduced the test data creation effort by 160 PD.
  ACE Chubb Integration:
  Implemented Automated Data Verification Mechanism for PRISM to MERIDIAN migration which will validate 1000’s of policy records in 2 hours.
Process Optimization
Test Execution
  UW Portal:
  UW Portal Regression Cycle is reduced to 3.5 days from the initial 5 days through parallel execution & test script optimization.
  Implemented Automated Premium Calculator to validate premium calculation mechanism in Underwriting Portal Programme (Property Australia & Brazil)
  Across All COG Programmes:
  Implemented Digital TV (Video based Training Material) for across programs and shared with business users for UAT / Production training.
  Implementing End to End Quality Dashboard which will provide Single View of Quality across all the phase of SDLC - Requirements, Design, Build, SIT and UAT.
The below section illustrates the key accomplishments achieved in Sep 2016 across Software Testing Lifecycle which will potentially improve the efficiency of the testing.
Improvement Levers

## Slide 7
UWP- Planned Continuous Improvement Initiatives
SHORT TERM 3 MONTHS | Regression Automation - Apollo Interface Verification using AUTO IT | Predicted - 50% effort saving per regression run. .
 | Parallel execution of Automation Scripts in different VDI | Predicted - 25% effort saving per regression run..
 | Automated Premium Calculator | Increase in test efficiency and accuracy.
 | Static Testing - Early Stage Requirements Validation | Early Identification of defects during the CR process / Requirements level
 | Web services Testing - SOAP UI Based testing (For new services) | Early identification of defects
MEDIUM TERM 6 MONTHS | Regression Automation - Genius Interface Verification - AUTO IT. | Predicted - 50% effort saving per regression run.
 | Increase in Risk Based Testing for Country / LOB Rollouts | Increase in Test Coverage & Effectiveness
 | Unhandled Automation Execution for Regression. | Predicted - 50% effort saving per regression run..
LONG TERM 9 MONTHS | Dynamic Content Validation for document verification. | Predicted - 50% effort saving per regression run.
 | Leveraging automation - functional testing for country rollouts. | Increase in Test Coverage
INITIATIVES
BENEFITS

## Slide 8
Innovation Dashboard 2016
UW Portal - Innovation Savings 2016
$43.18 K
190 PD
Effort Savings
Cost Savings
WorkView - Innovation Savings 2016
$156.90 K
692 PD
Effort Savings
Cost Savings
High Impact Innovations
Data Interface E2E
Automated Testing
  An Automated widget to extract the data elements from source flat files (OMNI, Genius, etc.) and compare data with WorkView
Automated End to End Image Interface Testing
  An End-to-End automated utility to test all the routing rules, and to check the data validation between the ack files, audit logs and in DB
Effort Saved: 80 PD
Effort Saved: 209 PD
Work View Digital TV
  Web based Digital TV enables the users to have a virtual demo of all the components and functionalities in WorkView.
Effort Saved: 68 PD
Chart: Cumulative Innovation Savings Cost (in $) - 2016
| Jan-16 | Feb-16 | Mar-16 | Apr-16 | May-16 | Jun-16 | Jul-16 | Aug-16 | Sep-16 | Oct-16 | Nov-16 | Dec-16
Impacted Cost | 7731.8267 | 15240.3333 | 23514.3067 | 39400.74 | 72265.29 | 108723.7025 | 151360.0695 | 200084.4845

## Slide 9
Appendix

## Slide 10
UW Portal - UAT Root Cause Analysis
UAT Defect Root Causes - By SIT team | Casualty Rollout PANAMA and CR 514 | Casualty Rollout NZ and CR 470 | CR 337 | CR 524 | Property UKI | Grand Total
SIT Team Improvement (Coverage or Regression Improvements) (2%) |  |  |  |  |  | 
Test Coverage Miss | 0 | 0 | 0 | 0 | 1 | 1
Regression Defects | 0 | 0 | 0 | 0 | 1 | 1
Improvement Area for BA’s/Business (10%) |  |  |  |  |  | 
CR / Enhancements / Requirement Changes | 11 | 0 | 0 | 0 | 1 | 12
Improvement Area for Environment / Code Deployment Process (36%) |  |  |  |  |  | 
UAT Only Defects - Happening only in UAT environment | 3 | 5 | 2 | 2 | 0 | 12
Environmental / Configuration Issue | 12 | 11 | 5 | 5 | 0 | 33
Sporadic Errors (Unexpected Errors / Communications Errors) | 0 | 0 | 1 | 0 | 0 | 1
Improvements Area for STLC Process (7%) |  |  |  |  |  | 
Existing SIT Defects - Duplicate of SIT Open Defects | 0 | 0 | 0 | 0 | 2 | 2
Existing Production Issue | 0 | 7 | 0 | 0 | 0 | 7
Improvements Area for UAT Users (45%) |  |  |  |  |  | 
Invalid & Duplicate Defects/Defect/Not Reproducible & Duplicate Defects | 15 | 9 | 3 | 2 | 28 | 57
Grand Total | 41 | 32 | 11 | 9 | 33 | 126

## Slide 11
QA Metrics- Definition
PHASE | TEST METRICS | UOM | DEFINITION
Test Design | Test Design Productivity | Nos. | (Overall Test Case Count/(Test Design Duration*Resource Count))
 | Test Design Coverage | % | ((Total number of testable requirements mapped to test case cases /(Total number of base lined testable requirements)*100)
 | Test Design Reusability | % | Re-used Test Cases/(Overall Test Cases*100)
Test Execution | Test Execution Productivity | Nos. | (Overall Test Case Executed/(Test Execution Duration*Resource Count))
 | Test Effectiveness | % | ((Total no of application defects found by Cognizant-Total number of application defects rejected by the customer)/( Total no of application defects found by Cognizant + Total number of application defects found by customer))*100
 | Test Execution Coverage | % | ((Total Number of test cases executed / Total Number of test cases scoped for testing)*100)
Quality Metrics | Error Discovery Rate | Rate | ((Total number of valid application defects) /Number of Test Cases executed (cumulative of the number of cycles executed) till the reporting period)
 | Quality of Fix | % | (Total no.of Defects reported as fixed - Total no. of reopened application Defects ) / (Total no.of Defects reported as fixed + Total no. of new application Defects due to fix)*100)
 | Defect Leakage | % | (Valid application Defects Reported by customer/ (Application Defects Found by Cognizant as part of Test Execution + Valid application Defects Reported by the customer)*100)
 | Overall Schedule Variance | % | ((Actual end date – Planned end date) / Planned duration) * 100)
 | Build Rejection | %. | (No.of Build Rejected/(Total No.of Build Deployed*100)

## Slide 12
Thank You